## Slide 1: PDS Build 11.0 Test Readiness Review
Richard Chen/Gary Chen
Jordan Padams/Thomas Loubrieu/Emily Law
10/26/2020

## Slide 2: Agenda
Review Board
Work Product Status
System Package Delivery Status
Test Objectives
Test Environment
Security Scan Results
Known Security Risks
Summary of Test Cases
Key Test Cases
Test Personnel
Test Effort
Testing Constraints and Risks
Action Item Status
Deviations
  Waivers
  Liens
  ECRs
  Other

## Slide 3: Review Board
Board
Customers
Chair | Scott Markham
Chief Engineer | Costin Radulescu
Assurance Engineer | Eva Bokor
Security Systems Engineer | Mike Pajevski
Task Manager | Jordan Padams
Test Engineer | Richard Chen / Gary Chen
N/A

## Slide 4: Work Product Status
Work Product | DMS Doc and Revision ID | DMS Document Status
Test Plan | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/Build%20Deliverables/Build%2011.1%20Deliverables/testPlan.20201022.pdf | Draft
PDS General System Software Requirements Document (SRD) version 1.1 | https://pds-engineering.jpl.nasa.gov/file/pds4-system-reqs.pdf-0 https://pds-engineering.jpl.nasa.gov/file/ds4-harvest-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-preparation-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-registry-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-report-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-search-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-security-design.pdf-0, as found on https://pds-engineering.jpl.nasa.gov/content/key-documents https://github.com/NASA-PDS-Incubator/pds-deep-archive/blob/master/docs/pds4_nssdca_delivery_design_20191219.docx and https://docs.google.com/spreadsheets/d/18oqtg3DEo2KrgvBOWLSOuqF2uZtq2XmByJwUknYSZUQ/edit#gid=1170315169 | Released
Test Procedures | To be developed after TRR | N/A
Test Anomaly & Issues (GitHub Issues) | Issues are tracked under each individual component repository, e. g. https://github.com/NASA-PDS-Incubator/validate/issues See Release Description for links to specific repositories. | Anomalies found during system test cycles. Task tracking.
Test Support Tools | N/A | N/A
Test Report | To be developed after testing is completed | N/A
System Deployment Guide | See individual tool Installation Guides. | N/A
Release Description | https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/rdd-11.0.0.html | N/A

## Slide 5: System Package Delivery Status
Software delivered for I&T as described in Release Description Document:
https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/rdd-11.0.0.html

## Slide 6: Test Objectives
Ensure modified tools are
  Functioning correctly
  Meeting user needs
  Meeting requirements

## Slide 7: Test Environment
The software tested can be run on any machine with sufficient resources. At EN:
  macbook running macOS 10.14.6, 32GB memory
  pds-int.jpl.nasa.gov, Linux 3.10.0, 8GB memory

## Slide 8: Modified Components
lddtool
validate
any machine
PDS operator
LDD
LDD,
metadata
metadata
doi service
registry / harvest
DOI
registration
Component | Description | Modifications
information-model (lddtool) | creates a local data dictionary (LDD) for a specialized domain such as a mission like Mars2020 or a discipline like Imaging, PDS’s base dictionary manifests the PDS Information Model. A dictionary takes the form of a schema and schematron rules. | 19 improvements, 7 fixes
validate | verifies the syntactic correctness of product labels against the base dictionary and optional local data dictionaries. | 4 improvements, 10 fixes, 9 requirements
registry / harvest | receives and serves metadata about PDS products | 11 improvements, 5 fixes, 17 requirements
deep-archive | creates Archive and Submission Information Packages (AIP, SIP) to be sent to NSSDC to archive data. | 7 improvements, 12 fixes, 10 requirements
doi service | manages DOIs, which have been requested for products such as PDS4 bundles and PDS3 data sets | 26 improvements, 2 fixes, 14 requirements
deep-archive
AIP,
SIP

## Slide 9: Summary of Test Cases
For this delivery, EN has separated the Test Plan from the Test Procedures, due to the large number of Modifications. Each item in the Test Plan, referenced earlier, maps 1-to-1 with an improvement, a fix, or an altered requirement in the RDD.

## Slide 10: Key Test Cases
pds-registry-app#38: the registry’s core functionality has moved from Solr to ElasticSearch, which should affect every test of the registry
pds-registry-app#8 and #9 each also introduces another technology and layer into the registry software
pds-doi-service#33 and any others that communicate with OSTI: this is a new interface for PDS.
validate#215: the functionality of checking the data’s number of records keeps coming back for fixes.

## Slide 11: Test Personnel
Person | Role(s) | Assignment(s) | FTE / Days
Richard Chen | Lead EN Tester | PDS EN I&T Lead | 1.0/15
Gary Chen | System Tester | PDS EN I&T | 1.0/15
Total |  |  | ?????

## Slide 12: Test Effort
# | Test ID | Mission | Tester | Days to Perform Test
1 | information-model (lddtool) | PDS | GChen | 10
2 | validate | PDS | GChen | 10
3 | registry / harvest | PDS | RChen | 15
4 | deep-archive | PDS | GChen | 5
5 | doi service | PDS | RChen | 10
 |  |  |  | Total days 50

## Slide 13: Testing Constraints & Risks
IF installation and configuration of external software packages goes poorly THEN testing of the registry will halt until solved WITH LIKELIHOOD OF 50%.
IF OSTI’s interface works poorly THEN many components of doi service will halt WITH LIKELIHOOD of 10%.
IF software changes and fixes come in THEN those tests will need to be rerun WITH LIKELIHOOD of 90% and CONSEQUENCE OF resetting the number of days needed for testing.

## Slide 14: Action Item Status
None

## Slide 15: Deviations
New “CCB” process defined with PDS Software Working Group
  Build 11.0 Deviations: https://github.com/NASA-PDS/pds-swg/issues?q=is%3Aissue+label%3AB11.0
Deviations
New PDS User Experience Tasks
  https://github.com/NASA-PDS/pds-swg/issues/1
Validate improvements deferred to build 11.1
  https://github.com/NASA-PDS/pds-swg/issues/2
PDS4 SCRs not received from DDWG
  Note: Working towards improved automated tracking of these for future builds

## Slide 16: Task realization metrics
Component | Task Planned | Task Planned realized | Total Tasks realized | Comment
PDS4 Information Model (lddtool) | 13 | 6 | 20 | Work dependent on receivables from DDWG*
LDD tools | 4 | 4 | N/A | 
Validate | 7 | 3 | 14 | Deferred
PDS4 jparser | 1 | 0 | 0 | Deferred
Registry | 13 | 10 | 16 | 
Deep archive | 2 | 2 | 19 | 
DOI service | 11 | 10 | 28 | 
Search | 2 | 2 | 2 | 
API | 4 | 4 | 8 | 
UX/Web Design | 0 | 0 | 7 | New task
*DDWG – PDS Data Design Working Group
Repos at https://github.com/NASA-PDS/

## Slide 17: Backup

## Slide 18: Known Security Risks
Known Security Vulnerabilities (java)
Need to update scan Info – Thomas to provide