## Slide 1: PDS Build 11.1 Test Readiness Review
Gary Chen/Richard Chen
Jordan Padams/Thomas Loubrieu/Emily Law
4/29/2021

## Slide 2: Agenda
Review Board
Work Product Status
System Package Delivery Status
Test Objectives
Test Environment
Security Scan Results
Known Security Risks
Summary of Test Cases
Key Test Cases
Test Personnel
Test Effort
Testing Constraints and Risks
Action Item Status
Deviations
  Waivers
  Liens
  ECRs
  Other

## Slide 3: Review Board
Board
Customers
Chair | Scott Markham
Chief Engineer | Costin Radulescu
Assurance Engineer | Eva Bokor
Security Systems Engineer | Mike Pajevski
Task Manager | Jordan Padams
Test Engineer | Richard Chen / Gary Chen
N/A

## Slide 4: Work Product Status
Work Product | DMS Doc and Revision ID | DMS Document Status
Test Plan | https://pds-engineering.jpl.nasa.gov/file/release_build_11.1_test_plan.docx | Version 1.0
PDS General System Software Requirements Document (SRD) version 1.1 | https://pds-engineering.jpl.nasa.gov/file/pds4-system-reqs.pdf-0 https://pds-engineering.jpl.nasa.gov/file/ds4-harvest-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-preparation-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-registry-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-report-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-search-design.pdf-0 https://pds-engineering.jpl.nasa.gov/file/pds4-security-design.pdf-0, as found on https://pds-engineering.jpl.nasa.gov/content/key-documents https://github.com/NASA-PDS-Incubator/pds-deep-archive/blob/master/docs/pds4_nssdca_delivery_design_20191219.docx and https://docs.google.com/spreadsheets/d/18oqtg3DEo2KrgvBOWLSOuqF2uZtq2XmByJwUknYSZUQ/edit#gid=1170315169 | Released
Test Procedures | To be developed after TRR | N/A
Test Anomaly & Issues (GitHub Issues) | Issues are tracked under each individual component repository, e. g. https://github.com/NASA-PDS See Release Description for links to specific repositories. | Anomalies found during system test cycles. Task tracking.
Test Support Tools | N/A | N/A
Test Report | To be developed after testing is completed | N/A
System Deployment Guide | See individual tool Installation Guides. | N/A
Release Description | https://nasa-pds.github.io/releases/11.1/rdd.html | N/A

## Slide 5: System Package Delivery Status
Software delivered for I&T as described in Release Description Document:
https://nasa-pds.github.io/releases/11.1/rdd.html

## Slide 6: Test Objectives
Ensure modified tools are
  Functioning correctly
  Meeting user needs
  Meeting requirements

## Slide 7: Test Environment
The software tested can be run on any machine with sufficient resources. At EN:
  macbook running macOS 10.14.6, 32GB memory
  pds-int.jpl.nasa.gov, Linux 3.10.0, 8GB memory
  Windows 10 Pro.

## Slide 8: Modified Components
lddtool
validate
any machine
PDS operator
LDD
LDD,
metadata
metadata
doi service
registry
DOI
registration
Component | Description | Modifications
information-model (lddtool) | creates a local data dictionary (LDD) for a specialized domain such as a mission like Mars2020 or a discipline like Imaging, PDS’s base dictionary manifests the PDS Information Model. A dictionary takes the form of a schema and schematron rules. | 7 improvements, 17 fixes
validate | verifies the syntactic correctness of product labels against the base dictionary and optional local data dictionaries. | 14 improvements, 25 fixes, 5 requirements
registry application | receives and serves metadata about PDS products | 24 improvements, 6 fixes, 10 requirements
deep-archive | creates Archive and Submission Information Packages (AIP, SIP) to be sent to NSSDC to archive data. | 2 improvements, 3 fixes, 1 requirements
doi service | manages DOIs, which have been requested for products such as PDS4 bundles and PDS3 data sets | 24 improvements, 11 fixes, 1 requirements
deep-archive
AIP,
SIP

## Slide 9: Summary of Test Cases
Each item in the Test Plan, referenced earlier, maps 1-to-1 with an improvement, a fix, or an altered requirement that is testable in the RDD.

## Slide 10: Key Test Cases
validate#189: Validate giving errors for large data file (>2 GB) which contains multiple binary tables.
There are 10 pds-doi-ui test cases, the web UI for pds-doi-service is new to I&T. Setting up the testing environment on different environment with limited documentation will take time and effort.
mi-label#10: The Windows version of mi-label version 1.1.2 does not work out-of-the-box. It is currently necessary for the user to manually edit line 52 of mi-label-1.1.2\bin\generate.bat.

## Slide 11: Test Personnel
Person | Role(s) | Assignment(s) | FTE / Days
Gary Chen | Lead EN I&T Tester | Lead PDS I&T | 1.0/20
Richard Chen | EN I&T Tester | Support PDS I&T | 1.0/20
Total |  |  | 40 days

## Slide 12: Test Effort
# | Test ID | Mission | Tester | Days to Perform Test
1 | information-model (lddtool) | PDS | GChen | 5
2 | validate | PDS | GChen | 10
3 | registry / harvest | PDS | RChen | 15
4 | deep-archive | PDS | GChen | 5
5 | doi service | PDS | RChen | 10
6 | doi ui | PDS | Gchen | 5
 |  |  |  | Total days 50

## Slide 13: Testing Constraints & Risks
IF installation and configuration of external software packages goes poorly THEN testing of the registry will halt until solved WITH LIKELIHOOD OF 50%.
IF OSTI’s interface works poorly THEN many components of doi service will halt WITH LIKELIHOOD of 10%.
IF software changes and fixes come in THEN those tests will need to be rerun WITH LIKELIHOOD of 90% and CONSEQUENCE OF resetting the number of days needed for testing.

## Slide 14: Action Item Status
None

## Slide 15: Deviations
“CCB” process defined with PDS Software Working Group
  Build 11.1 Deviations: https://github.com/NASA-PDS/pds-swg/issues?q=label%3AB11.1+label%3Achange-request
Deviations

## Slide 16: Task realization metrics
Component | Task Planned | Task Planned realized | Total Tasks realized | Comment
PDS4 Information Model (lddtool) | 8 | 6 | 24 | 
Validate | 13 | 13 | 39 | 
PDS4 jparser | 1 | 1 | 4 | 
Registry | 22 | 17 | 25 | Deployment on AWS a bit slower than foreseen
API | 22 | 11 | 16 | Re-focus on demo with notebook
Deep archive | 1 | 1 | 6 | 
DOI service | 20 | 16 | 36 | Add table view in UI as entry point prevent from completing the documentation actions.
UX/Web Design | 29 | 3 | 15 | Change plan due to creation of PDS-wide working group
Tracking service | 5 | 1 | 3 | Over estimation of what/quality of existing software
Repos at https://github.com/NASA-PDS/

## Slide 17: Backup