## Slide 1: PDS Engineering Node (EN) Delivery & Deployment Review
Jordan Padams, Richard Chen, Gary Chen, Emily Law, Thomas Loubrieu
December 10, 2020

## Slide 2: Agenda
Review Board
Software Overview
Work Product Status
Requirements
Improvements
Defect Corrections
Test Status Summary
Test Case Explanation(s)
Unverified Requirements
Unverified Improvements
Unverified Defect Corrections
Software Status
Open Defect Summary
Open CRIT 1 & 2 Defects
Action Item Status
Deviation Summary
Deviations
  Waivers & Liens
  ECRs
  Other
Backup
  Test Objectives
  Test Environment
  Key Test Cases

## Slide 3: Review Board
Board
Customers
Chair | Robin O’Brien
Chief Engineer | Costin Radulescu
Assurance Engineer | Korwin Anderson
Security Systems Engineer | Mike Pajevski
Task Manager | Jordan Padams
Task Cognizant Engineer | Thomas Loubrieu
N/A – PDS EN will present an overview of these
slides to PDS Software Working Group

## Slide 4: Software Overview
The Planetary Data System (PDS) is NASA’s official planetary data long term archive.
  For more information on the PDS, see our website: https://pds.nasa.gov/home/about/
In addition to PDS website, PDS Engineering Node is responsible for PDS4, PDS Information Model, and a suite of PDS4 system services and tools that support PDS data lifecycle.
  For more information on the PDS Engineering Node, see our website: https://pds-engineering.jpl.nasa.gov/
Build 11.0 made a number of improvements for Information Model 1.15.0 and tools including
  Registry App, DOI Service, Deep Archive, Validate, PDS4 JParser, Transform
In addition, it fixed a number issues found in previous builds.

## Slide 5: Known Issues
The following details known details missing from the review material:
Section | Description
Improvements and Bug Counters | Our current reporting mechanisms do not enable autonomous counters for issue tracking.
SLOC Counts | We do not currently have SLOC counters or code coverage setup for our repositories.
Identifying Test-worth Improvements / Bug Fixes | RDD does not sufficiently identify high priority / criticality improvements / bugs to test
Traceability between Release Plan and RDD | Insufficient mapping of those tasks identified as part of release plan versus what winds up in the RDD

## Slide 6: Work Product Status
Document Title | DMS Doc and Revision ID
Management Plan | https://pds-eng ineering.jpl.nasa.gov/sites/default/files/documents/pds2010/keydocuments/PDS-SMP.pdf
Task Implementation Plan | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/pds2010/pds4-proj-plan-07172013.pdf
Release Plan | https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/plan-11.0.0.html
Operation Concept | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/pds2010/keydocuments/pds4-ops-concept.pdf
Requirements | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/pds2010/design/system_design/pds4_system_reqs.pdf
Architecture Description | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/pds2010/architecture/system_architecture/pds4_system_arch_spec.pdf
Design Specification | See various design docs in: https://pds-engineering.jpl.nasa.gov/content/key-documents
Interface Specification | N/A
Test Plan | pds-engineering.jpl.nasa.gov/sites/default/files/testPlan.20201022.docx
Test Procedures | pds-engineering.jpl.nasa.gov/file/testProcs_20201206.docx
Release Description | https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/rdd-11.0.0.html
Product Guide | N/A
User Guide | See individual tool documentation. Links in RDD
Test Report | https://pds-engineering.jpl.nasa.gov/sites/default/files/documents/Build%20Deliverables/Build%2011.1%20Deliverables/testProcs_20201206.docx

## Slide 7: Test Status Summary
Metric | Value
Total Number of Tests | 64
Successful Tests | 62
Partially Successful Tests | 2
Tests in Progress | 0
Unsuccessful Tests | 0
Unexecuted Tests | 0

## Slide 8: Improvements
Summary of Significant Improvements
pds-registry-app#38 - replacement of underlying database / search engine
pds-doi-service#46 - Implement the command line and parser to release a doi
pds-registry-app#54 - The service should be scalable to enable publishing and management of up to 100 million registrations
validate#63 - Validate Table_Character groups and their specified lengths match the specified group_length
Total number of new improvements | 75
For requirements tracing, see tickets.
To view all improvements, see RDD: https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/rdd-11.0.0.html

## Slide 9: Defect Corrections
Summary of Significant Defect Fixes
validate#149 - Update software to check number of records specified in label matches the records in the table
validate#219 - validate v1.22.3 has large performance degradation on products with many tables
validate#234 - Validate gives incorrect records mismatch WARNING for interleaved data objects
pds-deep-archive#29 - SIP and Transfer Manifest duplicate files and LIDVIDs
pds4-information-model#227 - LDDTool: erroneously replaces TBD values with null in JSON output
pds4-information-model#180 - LDDTool does not handle "unbounded" maximum cardinality in Choice blocks correctly
Total number of new defect corrections | 59
For requirements tracing, see tickets.
To view all bugs, see RDD: https://pds-engineering.jpl.nasa.gov/development/pds4/11.0.0/release/rdd-11.0.0.html

## Slide 10: Requirements
ID | Requirement Statement | Procedure Test ID | Requester
1 | PDS Registry * | HVT.* | PDS
2 | PDS DOI Service | DOI.* | PDS
3 | PDS Deep Archive | DEEP.* | PDS
4 | Validate | VAL.* | PDS
5 | PDS4 Information Model | SCMA.* | PDS
Total number of new requirements | 49

## Slide 11: Failed Test Case 1
Test Case VAL.8, steps 9 and 10
  Description: Test various capabilities described in release 11.0
  Result: Partial Pass
  Issues:
    https://github.com/NASA-PDS/validate/issues/217 is one of many issues for the same problem, content checking the length of tables. 3 test labels exist for each of 15 combinations of File_Area_* and Table_*: 1 with num_records too low for the data, 1 too high, 1 just right - validate should throw a warning, an error, and nothing. However, validate on the 45 labels throws 0 warnings and 10 errors.
    https://github.com/NASA-PDS/validate/issues/188 Errors with heterogeneous root tags and prologs. When, in a single run, validating a number of labels with heterogeneous root tags and prologs, validate may incorrectly report errors that it would not report if the files were validated individually. Having heterogeneous and conflicting root tags in a single validation run is unlikely.

## Slide 12: Failed Test Case 2
Test Case VAL.9
  Description: Test various capabilities described in release 10b
  Result: Fail
  Issue:
    https://github.com/NASA-PDS/validate/issues/222: Reduce error messages for overlapping fields. The number of error messages remains high.

## Slide 13: Unverified Requirements
Requirement ID | Requirement Statement | Rationale for not Verifying
pds-deep-archive#47 | Generate from Registry | Not implemented
pds-deep-archive#51 | Use checksum manifest instead of registry | Not implemented
pds-doi-service#8 | Able to deactivate DOI | Not implemented
pds-doi-service#16 | Manage DOIs through DataCite | Not implemented
pds-doi-service#35 | Produce Status Report | Not implemented
pds-registry-app#66 | Require authorization for updating registry | Not implemented
pds-registry-app#68 | Require checksums | Not implemented.
validate#239 | Verify directory naming standards | Not implemented
validate#247 | Accept inputs to locate schemas | Not implemented
validate#248 | Verify that only one label references a file | Not implemented

## Slide 14: Unverified Improvements
Improvement ID | Improvement Statement | Rationale for not Verifying
pds-doi-service#1 | Develop initial requirements and design | No external manifestation
pds-doi-service#2 | Create/draft DOI object capability | No external manifestation
pds-doi-service#19 | Design REST API and JSON response | No external manifestation
pds-doi-service#20 | Develop draft PDS Policy for Assigning DOIs | No external manifestation
pds-doi-service#28 | Meet coding standards | No external manifestation
pds-doi-service#40 | Develop operational documentation and test suite | No external manifestation
pds-doi-service#41 | Develop simple regression test suite for deployment | No external manifestation
pds-doi-service#44 | Perform benchmark tests | No external manifestation
pds-doi-service#65 | Revise DOI Service Requirements | No external manifestation
pds-doi-service#71 | Initialize production deployment with pre-existing DOIs | No external manifestation
pds-doi-service#82 | End to end behave test | No external manifestation

## Slide 15: Unverified Improvements
Improvement ID | Improvement Statement | Rationale for not Verifying
pds-registry-mgr-elastic#3 | Implement Authentication | Not worth overcoming difficulty with pds-int
pds4-information-model#87 | Enhance software error handling | No external manifestation
pds4-information-model#158 | Set up CI/CD and nightly builds | No external manifestation
pds4-information-model#165 | Streamline process for changing legal values | No external manifestation
pds4-information-model#166 | GeoTIFF format as operational PDS4 image | Not implemented
pds-registry-app#8 | Design & implement Multi-Node deployment | Not worth overcoming difficulty with pds-int
pds-registry-app#9 | Design & implement Security and Authorization | Not worth overcoming difficulty with pds-int
pds-registry-app#11 | Develop Registry reporting/visualization | Not implemented
pds-registry-app#20 | Update Schema Generator for special cases | No external manifestation
pds-registry-app#38 | Study Solr vs ElasticSearch | No manifestation. Or all tests demo latter

## Slide 16: Unverified Defect Corrections
Defect ID | Defect Summary | Rationale for not verifying
pds-deep-archive#82 | Output SIP has backslashes on Windows | No good access to PC
pds-registry-mgr-elastic#7 | Update-schema command fails | No external manifestation
pds-registry-app#3 | Doesn’t build on Windows | No good access to PC
pds-registry-app#5 | Installation documentation insufficient | No external manifestation
pds-registry-app#21 | Can’t build application due to file size limit | No external manifestation
validate#203 | Assembly plugin non-fatal errors on Windows | No external manifestation
validate#219 | performance degradation if many tables | Hard test to create

## Slide 17: Software Status
SLOC and Code Coverage not currently generated by PDS CI/CD
Tentatively planned for FY21

## Slide 18: Open Defect Summary
Metric | Prior DDR | This DDR
Defects Opened in Cycle | 34 | 11
Defects Closed in Cycle | 44 | 59
Open Criticality 1 Defects | UNK | 0
Open Criticality 2 Defects | UNK | 0
Open Criticality 3 Defects | UNK | 18
Open Criticality 4 Defects | UNK | 42
Open Unassigned Criticality Defects | UNK | 0

## Slide 19: Open CRIT 1 & 2 Defects
Issue | Criticality | Workaround
None |  | 

## Slide 20: Action Item Status
No formal Request for Actions from TRR

## Slide 21: Deviations
New “CCB” process defined with PDS Software Working Group
  Build 11.0 Deviations: https://github.com/NASA-PDS/pds-swg/issues?q=is%3Aissue+label%3AB11.0
Deviations
New PDS User Experience Tasks
  https://github.com/NASA-PDS/pds-swg/issues/1
Validate improvements deferred to build 11.1
  https://github.com/NASA-PDS/pds-swg/issues/2
PDS4 SCRs not received from DDWG
  Note: Working towards improved automated tracking of these for future builds

## Slide 22: Deviation Summary
Component | Planned | Planned + Realized | Added | Total Tasks realized | Comment
PDS4 Information Model (LDDTool) | 13 | 6 | 14 | 20 | Work dependent on receivables from DDWG*
LDD Management | 4 | 4 | 0 | 4 | 
Validate | 7 | 3 | 11 | 14 | Deferred incomplete tasks
PDS4 JParser | 1 | 0 | 0 | 0 | Deferred
Registry | 13 | 10 | 6 | 16 | Added tasks were extensions of planned tasks
PDS Deep Archive | 2 | 2 | 17 | 19 | Added tasks were extensions of planned tasks
DOI Service | 11 | 10 | 18 | 28 | Added tasks were extensions of planned tasks
Search | 2 | 2 | 0 | 2 | 
PDS API | 4 | 4 | 4 | 8 | 
UX/Web Design | 0 | 0 | 7 | 7 | New task
*DDWG – PDS Data Design Working Group
Repos at https://github.com/NASA-PDS/

## Slide 23: Deviations
Removed from Release Plan:
Update Validate to handle additional File_Areas added after original implementation - NASA-PDS/validate#229
Update Validate and PDS4 JParser to better handle additional data types - NASA-PDS/validate#212
Fix bug where caching is not sufficiently recognizing dictionary versions - NASA-PDS/validate#188
Update validate per SR requirements for collection inventories - NASA-PDS/validate#230
Added to Release Plan:
Perform User Interviews - NASA-PDS/PDS.nasa.gov-UX#1
Perform heuristic analysis from existing metrics - NASA-PDS/PDS.nasa.gov-UX#2
Formulate user stories - NASA-PDS/PDS.nasa.gov-UX#3
Identify opportunities for improvement with PDS web integration - NASA-PDS/PDS.nasa.gov-UX#4
Synthesize interview results into user research knowledge base - NASA-PDS/PDS.nasa.gov-UX#5
Model workflows and initial design directions based upon user analysis - NASA-PDS/PDS.nasa.gov-UX#6
Develop tailored PDS design system - NASA-PDS/PDS.nasa.gov-UX#7
Design mockups and develop prototype - NASA-PDS/PDS.nasa.gov-UX#8
https://github.com/NASA-PDS/pds-swg/issues/1
https://github.com/NASA-PDS/pds-swg/issues/2

## Slide 24: Backup

## Slide 25: Test Objectives
Describe the objectives of the test effort.
  You are communicating with the customer. This should indicate to the customer why the release is acceptable to use.

## Slide 26: Test Environment
Describe the test environment (may require multiple slides).
Briefly describe the affect that the differences between the build and test environments will have. If none, state so.
Describe each test environment. A Figure generally should be included of the network topology and the services provided by each node in the network.

## Slide 27: Key Test Cases
Describe the key/new test cases.
Test Case 1
Test Case 2
…

## Slide 28: Software Status
Component | Code Size | SLOC Added | SLOC Deleted | SLOC Changed | Code Coverage
Explain whether the SLOC measures are logical, actual, and with or without comments.
Package | ICA ID
Binary Release | 
Source Release | 
CM Tool | CM Repository (Repositories)
Jordan to fill out

## Slide 29: Defect List

## Slide 30: Deviations
Describe each deviation from planning documents (See MIMTaR A-12).
  Identify the applicable waivers, liens, and ECRs documenting process and product deviations.
  Identify additional deviations. For these, identify the rationale for the unapproved changes.
  However, exclude deviations related to CRIT-3 and CRIT-4 defect corrections.
For each deviation identify: (a) its type (e.g., requirement deviation); (b) its unique identifier; (c) its current status (and future plan); and (d) and provide a summary description of it. Add new columns as desired to the following table.
ID | Summary Statement
Jordan to fill out