## Sheet1
2018 PDS Tech Session (Feb 13-15) Action Items
Feb 13 Actions | Responsible Party | Target Date | Status | Comment
Make procedure for registering bundles and collections publicly available | EN | 2018-05-01 |  | Sean to work with Richard and Emily.
Email to NSSDCA to clarify when bundles go to NSSDCA and discuss backup of migrated PDS4 data | Morgan | 2018-02-13 | Done | need a policy on PDS4 migration deliveries to NSSDC?
Work a single solution for referencing PDS3 labels during migration to PDS4 | DDWG | TBD |  | Susie to submit an SCR by Mar 2
Lead a discussion on how we would merge PDS4 labels with PDS3 volumes as an approach to do migrations without duplicating products where the data format does not change | Susie | 2018-02-14 | Done
Develop a way to notify PDS and the public when new LDDs are being released | EN | 2018-09-30 |  | Target for Build 9a. Incorporate in Tracking Service.
Develop a robust testing program for discipline dictionaries; details need to be discussed and implemented. | DDWG | TBD |  | LDDTool is the first hurdle of testing followed by additional LDD specific tests.
Study Raugh's slides, which are posted on-line, in preparation for 2/14's discussion on LDD 'solutions' | Tech Session attendees | 2018-02-13 | Done
Send DDWG chair list of structures in PDS3 holdings that cannot be described using the FDSs in the current PDS4 model and estimation of their frequency of occurrence | Nodes | 2018-03-31 |  | Only things allow in PDS4
Determine which schema referencing scenario is appropriate for acceptance testing of a bundle during validation | TBD | TBD
Submit a S/W JIRA issue that a warning be issued in validate tool when the label and IM are mismatched | Lyle | 2018-02-28 | Done
Provide links to more granular tools information inside the tool documentation on the public facing page for each tool | EN / WITT | 2018-07-30 |  | Action to Mike and Sean to beef up the about pages for each tool so they better describe the tool's functions. This will be the content we use on the tool-specific pages of the web site. Consider prototype for MC meeting in April.
Make sure that all of the material that Nikki collected from the previous efforts of the PDS is already located on the training website | Maria | 2018-02-28
Feb 14 Actions | Responsible Party | Target Date | Status | Comment
Prototype how to help a user easily navigate the namespaces and find the relevant dictionaries in the correct versions | WITT | 2018-07-30 |  | Schema Page should be reorganized by IM number and not by dictionary
Submit SCRs to standardize building LDDs using LDDTool without hand editing | Mitch |  | Done | First, implement and demonstrate the various upgrades and changes to be made to LDDTool. Will determine if policy, standards reference or requirements be in place later to support this.
Submit SCR to change Ingest_LDD class to include IM and mod history | Mitch |  | Done
Include posting calendar with deadlines for each release for all builds including point builds | EN/WITT | 2018-04-01 |  | Present the issue to the WITT in an upcoming meeting.
Obtain access to PDS GitHub by sending request to Sean | DD stewards | TBD
Provide procedures on how to organize and desposit LDDs into PDS GitHub | Todd | 2018-03-31
Test migrated PDS3 bundles with Harvestor and report results to ensure it provides necessary support | Susie, Lyle | 2018-03-31
Assemble a working group to review mapping strategy and search field naming rules prior to Build 9a | Sean | 2018-05-31
Feb 15 Actions | Responsible Party | Target Date | Status | Comment
Organize 1 day stewards meeting in conjunction with April MC F2F to discuss consistent schematron rules, dictionary validation, etc. | Anne | 2018-02-28
Develop a procedure to ingest project dictionaries and integrating them into the system bundle | EN | 2018-05-31 |  | Somewhat related to mission and discipline dictionaries showing up in the Data Dictionary Search.
Develop a simple set of best practices for constructing context products and pass it onto DDWG | Mitch | 2018-03-31
Review tech session notes and provide update to Emily | Tech Session attendees | 2018-02-23 | Done